## Frei Bid vs Invoices
# | Description | Bid Qty | Unit | Bid Rate | Bid Total | Inv 2644 (due 7/2) | Billed to date | Invoice 2647 | Notes | Invoice 2644
FOOTINGS & WALLS
1 | Mobilization / Admin / Layout | 1 | LS | 4000 | 4000 | 1000 | 1000 | 3000 | 25% draw
2 | Footings 18x12 | 402 | LF | 26 | 10452 | 11180 | 11180 | -728 | OVERAGE: billed 430 LF (+28)
3 | Footings 30x12 | 293 | LF | 34.37 | 10070.41 |  |  | 10070.41
4 | Interior Footings 18x12 | 57 | LF | 22 | 1254 |  |  | 1254
5 | Interior Footings 30x12 | 94 | LF | 29 | 2726 |  |  | 2726
6 | Spread Footing 24x24x12 | 3 | EA | 123 | 369 | 369 | 369 | 0
7 | Spread Footing 30x30x12 | 2 | EA | 167 | 334 | 334 | 334 | 0
8 | Spread Footing 36x36x12 | 4 | EA | 210 | 840 | 840 | 840 | 0
9 | Spread Footing 42x42x12 | 6 | EA | 270 | 1620 | 1620 | 1620 | 0
10 | Spread Footing 48x48x12 | 2 | EA | 330 | 660 | 660 | 660 | 0
11 | Spread Footing 60x60x12 | 9 | EA | 490 | 4410 | 2450 | 2450 | 1960 | billed 5 of 9
12 | Spot Footing 36x36x12 | 2 | EA | 330 | 660 | 660 | 660 | 0
13 | Spot Footing 42x42x12 | 1 | EA | 415 | 415 | 415 | 415 | 0
14 | Spot Footing 48x48x12 | 1 | EA | 500 | 500 | 500 | 500 | 0
15 | Spot Footing 60x60x12 | 2 | EA | 700 | 1400 |  |  | 1400
16 | Footing Steps | 0 | EA | 75 | 0 |  |  | 0
17 | Round Walls | 0 | EA | 150 | 0 |  |  | 0
18 | 24" Stem Wall | 406 | LF | 34 | 13804 |  |  | 13804
19 | 13' x 8" Foundation Wall | 107 | LF | 195 | 20865 |  |  | 20865
20 | 10' x 8" Foundation Wall | 236 | LF | 135 | 31860 |  |  | 31860
21 | Corner Charge | 31 | EA | 35 | 1085 |  |  | 1085
22 | Wall Corner Charge | 12 | EA | 45 | 540 |  |  | 540
23 | Popouts | 1 | EA | 125 | 125 |  |  | 125
SLABS
24 | Basement Floor Slab w/ #3 Rebar Mat | 2181 | SF | 6.7 | 14612.7 | 15852.2 | 15852.2 | -1239.5 | OVERAGE: billed 2,366 SF (+185)
25 | Main Floor Slab w/ #3 Rebar Mat | 2600 | SF | 6.7 | 17420 |  |  | 17420
26 | Rim Forming | 178 | LF | 8 | 1424 | 1424 | 1424 | 0
27 | Suspended 8" Floor Slab / B-deck | 1180 | SF | 26.25 | 30975 | 11800 | 11800 | 19175 | partial draw (lump 11,800)
28 | Garage Stemwalls | 72 | LF | 24 | 1728 |  |  | 1728
29 | Garage Slab w/ #3 Rebar Mat | 1766 | SF | 6.65 | 11743.9 |  |  | 11743.9
30 | Soft Cut Garage Slab | 1 | LS | 600 | 600 |  |  | 600
31 | Sunken Shower | 0 | EA | 350 | 0 |  |  | 0
32 | Hold Downs STHD 10 | 6 | EA | 30 | 180 |  |  | 180
33 | Hold Downs STHD 14 | 0 | EA | 45 | 0 |  |  | 0
34 | Bolts for Strong Walls | 4 | EA | 250 | 1000 |  |  | 1000
CONCRETE PUMPING
35 | Pumping - Basement Footings | 1 | LS | 1400 | 1400 |  |  | 1400
36 | Pumping - Basement Walls | 1 | LS | 1800 | 1800 |  |  | 1800
37 | Pumping - Basement Slab | 1 | LS | 1500 | 1500 | 1500 | 1500 | 0
38 | Pumping - Main Slab | 1 | LS | 1500 | 1500 |  |  | 1500
39 | Pumping - Suspended Slab | 1 | LS | 1100 | 1100 | 1100 | 1100 | 0
SITE / MISC
40 | Wash Out Pit | 5 | EA | 350 | 1750 |  |  | 1750
41 | Gradable Fill | 1 | LS | 650 | 650 |  |  | 650
42 | Skid Loader Rough Grading | 6 | HR | 110 | 660 |  |  | 660
43 | HV/AC in Slab (if needed) | 0 | LS | 1500 | 0 |  |  | 0
44 | Back Fill Plumbing | 0 | LS | 300 | 0 |  |  | 0
EXTRAS / NOT IN ORIGINAL BID
| Vapor Barrier 15 mil | 2366 | SF | 0.75 |  | 1774.5 | 1774.5 |  | extra
| Expansion (fiber) | 45 | EA | 5.01 |  | 225.45 | 225.45 |  | extra
| 1" Ramset Concrete Nails | 2 | EA | 25 |  | 50 | 50 |  | extra
| Labor | 12 | HR | 65 |  | 780 | 780 |  | extra
| Labor - pull/reset footings, retie rebar | 64 | HR | 65 |  | 4160 | 4160 |  | extra
| Additional Concrete at Spot Footings | 1 | LS | 220 |  | 220 | 220 |  | extra
| Cantilever Edge @ Suspended Slab | 178 | LF | 2.5 |  | 445 | 445 |  | extra
| CONTRACT (signed subcontract) |  |  |  | 198333.01
| Estimate 19643 line total |  |  |  | 198033.01 |  |  |  | est PDF; $300 diff = plumbing line
| Invoice 2644 total |  |  |  |  | 59359.15 | 59359.15 |  | due 7/2/2026
| Billed to date | [5 empty] | 59359.15 | 138973.86 | remaining vs contract
Invoice Totals
| Billed to date vs Contract | [9 empty] | remaining vs contract