## Sunpro
# | Description | Bid Qty | Unit | Bid Rate | Bid Total | Inv 3890718 (6/29/26) | Inv 3891720 (6/29/26) | Inv 3894241 (7/1/26) | Inv 3900730 (due 8/9/26) | Credit 255676 (7/30/26) | Inv 3920799 (7/30/26) | Inv 3921247 (due 8/31/26) | Inv 3897876 (due 8/6/26) | Inv 3899137 (due 8/7/26) | Inv 3899710 (due 8/8/26) | Inv 3902213 (due 8/10/26) | Inv 3907414 (due 8/16/26) | Credit 257064 (8/20/26) | Billed to date | Remaining vs bid | Notes
MATERIALS PACKAGE
1 | Lumber package | 1 | LS | 75000 | 75000 | 4531.05 | [12 empty] | 4531.05 | 70468.95 | Inv 3890718 (6/29/26): framing lumber pkg — studs, plates, T&G OSB, LSL band board, Simpson pins, delivery+fuel. $4,251.31 + $279.74 tax = $4,531.05. Job 746 Liberty Lane, SO 19267935. Due 7/30/26.
2 | Door package | 1 | LS | 31350 | 31350 | [13 empty] | 0 | 31350
3 | Truss package | 1 | LS | 62200 | 62200 |  | 3100 | [9 empty] | 40400 |  | 43500 | 18700 | Inv 3891720 (6/29/26): main floor truss package #254084-MF, PO 254084-MF. $2,919.79 + $180.21 tax = $3,100.00. Job 746 Liberty Lane, SO 19232240. Due 7/30/26. Inv 3907414 (7/16/26): upper floor truss package #254084-UF plus delivery for 746 Liberty Lane, $37,861.24 + $2,538.76 tax = $40,400.00, due 8/16/26.
4 | Base & Case | 1 | LS | 5500 | 5500 | [13 empty] | 0 | 5500
5 | Hardware | 1 | LS | 5500 | 5500 |  |  | 93 | 27.74 | -2162.05 | 2162.05 | 2162.05 | 4030.29 | 1962.25 | 131.4 | 128.61 |  | -3447.8 | 5087.54 | 412.46 | Inv 3894241 (7/1/26): Simpson SDS wood screws box, $87.12 + $5.88 tax = $93.00. Job 746 Liberty Lane. Due 8/1/26. Credit 255676 (7/30/26): price-correction credit against invoice 3920799 / order 19430770, rebar, strap tie holdowns, anchor bolts, and bearing plates, total credit $2,162.05. Inv 3920799 (7/30/26): same materials delivered to 746 Liberty Lane, $2,025.34 + $136.71 tax = $2,162.05, due 8/30/26. Inv 3921247 (7/31/26): corrected payable hardware and rebar invoice after the 7/30 invoice/credit pair; rebar, strap tie holdowns, anchor bolts, and bearing plates for 746 Liberty Lane. $2,025.34 + $136.71 tax = $2,162.05, due 8/31/26. Inv 3897876 (7/6/26): Simpson strong-wall anchor bolt/templates plus delivery/fuel for 746 Liberty Lane, $3,783.55 + $246.74 tax = $4,030.29, due 8/6/26. Inv 3899137 (7/7/26): Sunpro material/delivery charge for 746 Liberty Lane, $1,844.23 + $118.02 tax = $1,962.25, due 8/7/26. Inv 3899710 (7/8/26): Sunpro material charge for 746 Liberty Lane, $123.09 + $8.31 tax = $131.40, due 8/8/26. Inv 3902213 (7/10/26): Sunpro material charge for 746 Liberty Lane, $120.48 + $8.13 tax = $128.61, due 8/10/26. Credit 257064 (8/20/26): return/credit against invoice 3897876 / order 19312055, Simpson Strong Wall shearwall materials for 746 Liberty Lane. Total credit $3,447.80 ($3,229.79 materials + $218.01 tax).
| CONTRACT TOTAL |  |  |  | 179550
| BILLED TO DATE |  |  |  |  | 4531.05 | 3100 | 93 | 27.74 | -2162.05 | 2162.05 | 2162.05 | 4030.29 | 1962.25 | 131.4 | 128.61 | 40400 | -3447.8 | 53118.59
| REMAINING ON CONTRACT | [17 empty] | 126431.41